## Task Status
Module | Issue | Start date | End date | Assigned To | Created by | Status | Comments
| Like on post | 2015-05-23 | 2015-05-23 | Sunil |  | Closed | Data clean up is required for the like count.
| Comment on post | 2015-05-23 | 2015-05-23 | Sunil |  | Closed | Data clean up is required for the comment count.
| Video -On thumbnail video should get open | 2015-05-23 | 2015-05-23 | Sunil |  | Closed
| Add Poll is pending only text is getting display. | 2015-05-23 |  | Sumeet |  | Open
| Search on board screen | 2015-05-23 |  | Sumeet |  | Open | Needs to be decided, what to search name or posts.
| Add Document | 2015-05-23 |  | Sumeet |  | Open | 1. Add document icon is proper. 2. Enter document name field is getting mapped to add document due to which user is not able to add name. 3. Restrict the size limit of the document.
| Add Event from the board | 2015-05-23 |  | Sumeet |  | Open | 1. In answer it is allowing user to select question "Are you going?" 2. After entering adding event; page is staying static and data is not getting deleted. 3. After getting one error message event is not getting added to the board.
| Update Profile | 2015-05-23 | 2015-05-23 | Sunil |  | Closed
| Back button is not working on all pages - Like details,comment details,gallery details | 2015-05-23 |  | Sumeet | AK | Open | Not able to reproduce. (All back will behave same in the entire application)
| After posting a comment key board is still staying in an open state. | 2015-05-23 | 2015-05-23 | Bhavin | AK | Closed
| After posting post,poll,event or document that text should be blank after succesfull post. | 2015-05-23 |  | Sumeet | AK | Closed
| In Every post "small text" is gettign displayed in the detailed view. | 2015-05-23 | 2015-05-23 | Sunil |  | Closed | AK: What is this? UI fix
| When I click on the number of Likes on the board, when it goes inside, other prople who have liked the post are not seen | 2015-05-23 | 2015-05-23 | Vipin | AK | Not reproducible
| When I type comment on the board, the type sriter doesnt hide | 2015-05-23 | 2015-05-23 | Sunil | AK | Closed
| When I type a new comment all my previous comments show the newest one | 2015-05-23 | 2015-05-23 | Vipin | AK | Not reproducible
| When favourited a post, I go to Favourites Tab, the new post is not seen | 2015-05-23 | 2015-05-23 | Vipin | AK | Open/Issue with web service
| Inside post, Comments cannot be typed | 2015-05-23 | 2015-05-23 | Sunil | AK | Closed
| When I click on the psot title, I dont go inside the post | 2015-05-23 |  | Vipin |  | Behaviour according to web. | AK:Cant we please make the change? Is this need to be done from our end (vipin)? will do
| When I click on '3favourites', it takes me to a new window which shows only 1 post | 2015-05-23 | 2015-05-23 | Vipin | AK | Open/Issue with web service
| The comments are appearing not in proper order. The latest should be shown at the bottom | 2015-05-23 |  | Sunil | AK | Open
| While commenting on board, I can type only twice. More than that, the comments are not seen. Further I click on the total number of comments, i takes me to the window where I see my typed comments but not in order | 2015-05-23 | 2015-05-23 | Vipin | AK | Not reproducible
| UI not replciating the web version | 2015-05-23 |  | Vipin | AK | Need more clarification | AK:Some Fine tunes are pending. Have sent the PPT but its not integrated fully. Can sort it over WhatsApp group chat
| Image gallery not seen | 2015-05-23 |  | Vipin | AK | Not reproducible | AK: This may get solved when we have new post functionality done. Cant check inserting image galleries
| Video playing not seen | 2015-05-23 |  | Sumeet | AK | Open | URL is now bind with the vidoe image.
| Document favourite image is not showing properly. | 2015-05-23 | 2015-05-23 | Sunil | AK | Closed | AK: The documents, as discussed with Sumeet, must open in our App only and not in a new window
| When adding a document on web by paresh his designation is getting changed. | 2015-05-23 |  | Vipin |  | Open
| Add URL from the board | 2015-05-23 |  | Sumeet |  | Open | Need to traverse to some other tab to get loaded from the server.
| Add Video from the board | 2015-05-23 |  | Sumeet |  | Open | Need to traverse to some other tab to get loaded from the server.
| Document set to favourite should move to fav screen. | 2015-05-23 |  | Sunil |  | Open | AK: Documents and posts both. webservice missing.
| Document Date alignment | 2015-05-23 | 2015-05-24 | Sunil |  | Closed
| UI design changes - Update profile | 2015-05-23 |  | Sunil |  | Open
| In alerts wrong profile is getting opened. | 2015-05-23 | 2015-05-24 | Sunil |  | Closed
| In alerts dash with date is there - need to remove. | 2015-05-23 | 2015-05-24 | Sunil |  | Closed
2015-05-24
New post | New post funtionality with Text | 2015-05-24 |  | Sumeet | AK | Open
New post | New post functionality with Image gallery | 2015-05-24 |  | Sumeet | AK | Open
New post | New post functionality with Poll | 2015-05-24 |  | Sumeet | AK | Open
New post | New post funtionality with Video | 2015-05-24 |  | Sumeet | AK | Open
New post | New post functionality with document | 2015-05-24 |  | Sumeet | AK | Open
Documents tab | UI needs to be done | 2015-05-24 |  | Sumeet | AK | Open
Post API's | Separate array of subordinates, peers and tls in one api call combined | 2015-05-26 |  | Vipin
| And designation array also in one api call. Probably in complete users detials | 2015-05-26 |  | Vipin
| I am sending the media files from the device in add document post, so please check if they are received on the server | 2015-05-26 |  | Vipin
| in comment post '1hrs ago' text should displayed if comment was entered 1hr ago | 5/24/15 | Open | Sunil
| Separate array of subordinates, peers and tls in one api call combined And designation array also in one api call Probably in complete user details |  | open | vipin
Todays work
| If profile image is not set and last name of employee is not set then image issue arises. Suppose we have Shifra as employee she does not have profile image and last name so image issue arising | 2015-05-26 | 2015-05-26 | Sunil |  | Closed
| app crash in Shifra's Profile because Lastname is not available | 2015-05-26 | 2015-05-26 | Sunil |  | Closed
| image of the video clip-->in Profile,Favorite and post detail | 2015-05-26 | 2015-05-26 | Sunil |  | Closed
| image gallery not working on profile page post and favourite | 2015-05-26 |  | Sunil |  | Open | Not sure whether we have to do this or summet.?
Today's(27-05-2015) Work status
| In image making all characters should be in Capita. I.e. in Bhavana it is coming bH. It should be BH instead. | 2015-05-27 | 2015-05-27 | Dhrumil |  | Closed
| App getting crashed when updating profile of bhavna. Or say the one who does not have last name | 2015-05-27 |  | Dhrumil |  | Open | If lastname is not passed the webserivce is returning the desired response. Same issue happeining at web end. Check for the webservice
| Check on profile page if internet is slow or not coming display message "No internet connection. Please try after sometime". It should not display with the null layout.. | 2015-05-27 |  | Bhavin |  | Open
| Docs are not getting displayed in app even if they are visible in webapp | 2015-05-27 |  | Dhrumil |  | Open | json response is diffrent from webapp
| Make the profile icon of appropriate size. Current one is coming to big. | 2015-05-27 |  | Dhrumil |  | Closed
| UI on docs not proper. All and star icon alignment is not proper | 2015-05-27 |  | Bhavin |  | Closed
| When posting a post with images, images are not visible | 2015-05-27 |  | Sumeet |  | Open | Consult sumeet
| Remove default text from the login screen. It should come with login icons given today. | 2015-05-27 |  | Dhrumil |  | Closed
| Latest post is not coming on top | 2015-05-27 |  | Dhrumil |  | Closed
| Location details and date not coming in event post even if I entered them | 2015-05-27 |  | Dhrumil |  | Open | In response we are not getting the required fields. So need to check the code while adding post event.. Posted from web then all data are coming
| Loading of data should be done everytime when I move from one menu option to another | 2015-05-27 |  | Bhavin |  | Open

## Sheet1
Project Name |  | ITS OUR APP
Client Name |  | Z-Aksys Solutions Pvt. Ltd
Sr | Module Name | Test Cases | Assigned To | Created By | Start Date | Status | End Date | Bug Type | Iteration | Comments
1 | Login | Please chage the logo. It should be "It's Our APP" logo. Once user loging in the system then depedning of the company logo will change. | Sunil, Sumeet | Jaiswar Vipin Kumar R | 21st May 2015 |  |  | Desiging
2 | Login | If user not having internet connection, the please show them "no internet connection" message in respactive of any screen | Sunil, Sumeet | Jaiswar Vipin Kumar R | 21st May 2015 |  |  | Functional
3 | Board | Like
4
| Settings | In "Update My Profile" unable to edit name because it slides up |  | Rahul Dagli |  |  |  | Functional
5 |  | Check icon and logo size and also box around spacing |  |  |  | Done
6 |  | Check all font size like Paresh Sukthankar headline and the spacing between photo baseline and Dddd |  |  |  | Done
7 |  | Check the spacing between text and like button text |  |  |  | Done
8 |  | Add the new updates button on refresh the page on every new update by employee |  |  |  | Done
9 |  | Remove the line |  |  |  | Done
10 |  | Please checking the spacing Between two boxes and card shadow design |  |  |  | Done
11 |  | Please check the bottom buttons going out on screen and also scroll on bottom. |  |  |  | Done
12 |  | Check spacing both grey boxes is not equal |  |  |  | Done
13 |  | Check the spacing between text and like button text |  |  |  | In Progress
14 |  | Please check the Calendar Icon and Font size also… |  |  |  | Done
15 |  | Shadow is looking very nice please increase the spacing between 2 boxes |  |  |  | Done
16 |  | Like, Comment, Favorites commands is not working |  |  |  | Done
17 | Inside post | When I click on the number of Likes on the board, when it goes inside, other prople who have liked the post are not seen | Sunil/Sumeet | Anil K | 2015-05-23 | Done
18 | Inside post | When you go to any page inside from the board, the back button on the top left doesnt work | Sunil/Sumeet | Anil K | 2015-05-23
19 | Board | When I type comment on the board, the type sriter doesnt hide | Sunil/Sumeet | Anil K | 2015-05-23 | Done
20 | Board/Inside post | When I type a new comment all my previous comments show the newest one | Sunil/Sumeet | Anil K | 2015-05-23 | Done
21 | Favourites | When favourited a post, I go to Favourites Tab, the new post is not seen | Sunil/Sumeet | Anil K | 2015-05-23 | Done
22 | Inside post | Inside post, Comments cannot be typed | Sunil/Sumeet | Anil K | 2015-05-23 | Done
23 | Board | When I click on the psot title, I dont go inside the post | Sunil/Sumeet | Anil K | 2015-05-23
24 | Post favourites | When I click on '3favourites', it takes me to a new window which shows only 1 post | Sunil/Sumeet | Anil K | 2015-05-23 | Done
25 | Post favourites | Back button not working properly. The hit area might needs to be increase. The moment i click on back, the search bar gets activated | Sunil/Sumeet | Anil K | 2015-05-23
26 | Inside post | The comments are appearing not in proper order. The latest should be shown at the bottom | Sunil/Sumeet | Anil K | 2015-05-23 | Done
27 | Board | While commenting on board, I can type only twice. More than that, the comments are not seen. Further I click on the total number of comments, i takes me to the window where I see my typed comments but not in order | Sunil/Sumeet | Anil K | 2015-05-23 | Done
28 | Comments | Alignment of text box with the send button of the post is not correct. Kindly check FB/or linked for an idea. Call in csae you haev a doubt
29 | Board | Whenever I log in, it shoudl show me the previous screen with 'New posts' link to scroll me to the top
30 | Board | UI not replciating the web version | Sunil/Sumeet | Anil K | 2015-05-23
31 | Board | Image gallery not seen | Sunil/Sumeet | Anil K | 2015-05-23
32 | Board | Video playing not seen | Sunil/Sumeet | Anil K | 2015-05-23 | Playing in new window. Cant it play in iframe
33 | Board | New event not seen | Sunil/Sumeet | Anil K | 2015-05-23

## user login
URL : http://itsourapp.com/hdfcbank/
Email | Password | Roles
Anil.Jaggia@z-aksys.in | a
arun.mohanty1@z-aksys.in | a
Karuppusamy.Natchimuthu@z-aksys.in | a
munish.mittal@z-aksys.in | a
nitin.chugh@z-aksys.in | a | HOD
Nusrat.Pathan@z-aksys.in | a
parag.rao@z-aksys.in | a
paresh.sukthankar@z-aksys.in | a | Admin( GR, GB and HOD)
pushkar.gupta@z-aksys.in | a
RajivShiv.Banerjee@z-aksys.in | a
Sameer.Ratolikar@z-aksys.in | a
smita.bhagat@z-aksys.in | a
Sherna.Dmello@z-aksys.in | a
Neeraj.Jha@z-aksys.in | a | GR, HOD
URL: http://z-aksys.net/zappk/
URL : http://z-aksys.net/zappk/
Email | Password | Roles
anil@z-aksys.com | a | Admin( GR, GB and HOD)
vipin@z-aksys.in | a | Admin( GR, GB and HOD)
sanket@z-aksys.in | a
vijay@z-aksys.in | a
navnath@z-aksys.in | a
sagar@z-aksys.in | a | HOD
ashwini.b@z-aksys.in | a | HOD
jaee@z-aksys.in | a
rahul@z-aksys.in | a
pradeep@z-aksys.in | a
shifra@z-aksys.com | a | HOD
karen@z-aksys.in | a